## Template risk register
Tool: Template Risk Register
This template risk register can be used as a basis for your organisation’s risk tracking. It is an example of how your organisation can track risks specific to genomics. Please adapt or incorporate it to suit the needs and processes of your health service. This template register is part of the Genomics and Your Hospital Toolkit. The complete toolkit, along with a guide on how to use this register, can be found at GenomicsToolkit.org.au © MGHA 2024. These materials were prepared by the Melbourne Genomics Health Alliance (MGHA) and are protected by copyright. We would like to acknowledge the expertise and knowledge of those who have contributed to the development of these materials. Reproduction or distribution of these materials without this notice is prohibited.
Organisational risk or Patient pathway risk | If patient pathway risk, step in pathway: | Potential Risk | Assessment of local impact - rank from 1 (LOW) to 5 (HIGH) | Agreed relevant local controls (see Tool: Potential Controls/Treatments for risk in tab 2 'potential controls') | Person responsible | Timeframe
Organisational Risk |  | Lack of role clarity including lack of single point accountability
Organisational Risk |  | Failure of integration across clinicians/steps
Organisational Risk |  | Failure to ensure coordinated introduction and quality review
Organisational Risk |  | Inability to appropriately resource effective end-to-end processes
Organisational Risk |  | Risks associated with not undertaking testing
Organisational Risk |  | Lack of clarity about financial costs of tests and whole care pathway
Organisational Risk |  | Lack of appropriately skilled, sufficient workforce
Organisational Risk |  | Insufficient/inappropriate governance of non-standard genomic care (i.e., genomic care still considered research or genomic care considered emerging practice)
Organisational Risk |  | Other:
Patient Risk | Step 1: Identification of patients who should be considered for genomic testing | Relevant patients not identified
Patient Risk | Step 1: Identification of patients who should be considered for genomic testing | Inappropriate test ordering
Patient Risk | Step 1: Identification of patients who should be considered for genomic testing | Urgency and/or complexity not clearly identified
Patient Risk | Step 1: Identification of patients who should be considered for genomic testing | Other:
Patient Risk | Step 2: Referral process for consideration of potential testing pathways | Complex patient not referred to expert clinician/department
Patient Risk | Step 2: Referral process for consideration of potential testing pathways | Referral processes not known, and patients not referred appropriately
Patient Risk | Step 2: Referral process for consideration of potential testing pathways | Lack of timely referral
Patient Risk | Step 2: Referral process for consideration of potential testing pathways | No referral option availability
Patient Risk | Step 2: Referral process for consideration of potential testing pathways | Other:
Patient Risk | Step 3: Consideration of genomic test options | Incorrect/inappropriate test ordered (e.g., incorrect gene list selected; test sent to research lab)
Patient Risk | Step 3: Consideration of genomic test options | Multiple tests being ordered where one might be sufficient to begin
Patient Risk | Step 3: Consideration of genomic test options | Lack of awareness about test logistics/test processes
Patient Risk | Step 3: Consideration of genomic test options | Other:
Patient Risk | Step 4: Assessing and undertaking consent; and legal implications | Clinician undertaking consent does not fully understand consent and legal implications
Patient Risk | Step 4: Assessing and undertaking consent; and legal implications | Patient not appropriately consented
Patient Risk | Step 4: Assessing and undertaking consent; and legal implications | Other:
Patient Risk | Step 5: Ordering genomic tests | Incorrect/inappropriate test ordered
Patient Risk | Step 5: Ordering genomic tests | Multiple tests being ordered where one might be sufficient
Patient Risk | Step 5: Ordering genomic tests | Lack of awareness about test logistics/test processes
Patient Risk | Step 5: Ordering genomic tests | Other:
Patient Risk | Step 6: Genomic test analysis | Poor quality of laboratory test (i.e., large numbers of variants of uncertain significance, classification of variants does not follow rigorous process)
Patient Risk | Step 6: Genomic test analysis | Poor reporting by laboratory
Patient Risk | Step 6: Genomic test analysis | Other:
Patient Risk | Step 7: Interpreting genomic test results | Missed result return to patient
Patient Risk | Step 7: Interpreting genomic test results | Misinterpretation of results by clinicians (e.g., over- or under-calling of variants of uncertain significance)
Patient Risk | Step 7: Interpreting genomic test results | Lack of clarity about management of incidental findings
Patient Risk | Step 7: Interpreting genomic test results | Underappreciation of the difference between quality/reporting from different laboratories
Patient Risk | Step 7: Interpreting genomic test results | Underappreciation of impact on family members
Patient Risk | Step 7: Interpreting genomic test results | Other:
Patient Risk | Step 8: Clinical application of genomic results in the context of an individual patient | Insufficient/inappropriate consideration of current treatment requirements
Patient Risk | Step 8: Clinical application of genomic results in the context of an individual patient | Insufficient consideration of governance of treatment options that are either emerging practice or research
Patient Risk | Step 8: Clinical application of genomic results in the context of an individual patient | Insufficient/inappropriate consideration of future assessment needs
Patient Risk | Step 8: Clinical application of genomic results in the context of an individual patient | Lack of appropriate communication about potential risks and next steps in management and support of extended family
Patient Risk | Step 8: Clinical application of genomic results in the context of an individual patient | Lack of resources/supports for devastating diagnosis
Patient Risk | Step 8: Clinical application of genomic results in the context of an individual patient | Other:
Patient Risk | Step 9: Family support considerations and requirements | Lack of expertise in family follow up requirements
Patient Risk | Step 9: Family support considerations and requirements | Lack of clarity about who is accountable for family management
Patient Risk | Step 9: Family support considerations and requirements | Other:

## Potential Controls
Tool: Potential Controls/Treatments for Risks
Potential controls and / or treatments for organisational and patient risks
For organisational risks | Documented roles and responsibilities at each step of care pathway
Documented roles and responsibilities for escalation of issues/concerns
Implementation of quality metrics and systems
Formation of genomics leadership group
Review of new tests/models of care by genomics leadership group
Benchmarking and horizon scanning for best practice
Completion of model of care assessment to ensure costs, equipment, and workforce needs known and completed
Completion of new genomic practice screening tool
For patient risks at Step 1: Identification of patients who should be considered for genomic testing | Clearly documented and agreed models of care
Credentialling and training of staff to ensure skills and knowledge in appropriate referral
Design of locally appropriate access to genomics expertise (e.g., genomic champions in clinical units, establishment of multi-disciplinary meetings, laboratory feedback or guardrails)
Clear escalation pathways for questions/concerns including organisational expert backup
For patient risks at Step 2: Referral process for consideration of potential testing pathways | Consideration of genomic care within broader hospital capability framework
Clearly documented and agreed models of care
Traffic light/flowchart systems
Credentialling and training of staff to ensure skills and knowledge in appropriate referral
Design of locally appropriate access to genomics expertise (e.g., genomic champions in clinical units, establishment of multi-disciplinary meetings, laboratory feedback or guardrails)
Clear escalation pathways for questions/concerns including organisational expert backup
For patient risks at Step 3: Consideration of genomic test options | Organisational review of new tests/models of care
Test ordering guardrails
Credentialling of practitioners
Effective models of care including test ordering process
Contracts with specific laboratories for cost-effectiveness
Sufficient pathology expertise
Effective, timely clinician-laboratory communication of key information
Ensuring use of NATA-accredited laboratory
Training and development of relevant staff to ensure skills and knowledge in appropriate test ordering
Design of locally appropriate access to genomics expertise (e.g., genomic champions in clinical units, establishment of multi-disciplinary meetings, laboratory feedback or guardrails)
Clear escalation pathways for questions/concerns including organisational expert backup
For patient risks at Step 4: Assessing and undertaking consent; and legal implications | Training and development of relevant staff to ensure skills and knowledge in appropriate test ordering
Credentialling and special scope of practice to provide standards for relevant practitioners
Organisational determination of who can order which tests and thus undertake consent (e.g., Junior Doctor needs Consultant approval)
Design of locally appropriate access to genomics expertise (e.g., genomic champions in clinical units, establishment of multi-disciplinary meetings, laboratory feedback or guardrails)
Clear escalation pathways for questions/concerns including organisational expert backup
Point-of-care resources for clinicians
For patient risks at Step 5: Ordering genomic tests | Effective models of care including test ordering process
Training and development of relevant staff to ensure skills and knowledge in appropriate test ordering
Credentialling and special scope of practice to provide standards for relevant practitioners
Organisational determination of who can order which tests and thus undertake consent (e.g., Junior Doctor needs Consultant approval)
Design of locally appropriate access to genomics expertise (e.g., genomic champions in clinical units, establishment of multi-disciplinary meetings, laboratory feedback or guardrails)
Clear escalation pathways for questions/concerns including organisational expert backup
Point-of-care resources for clinicians
For patient risks at Step 6: Genomic test analysis | Effective models of care including test analysis
Credentialling of practitioners
(If external) contracts specifies quality metrics for test analysis
Sufficient pathology expertise
Ensuring use of NATA-accredited laboratory
For patient risks at Step 7: Interpreting genomic test results | Effective models of care including test return and test return monitoring
Training and development of relevant staff to ensure skills and knowledge in appropriate test ordering
Credentialling and special scope of practice to provide standards for relevant practitioner
Design of locally appropriate access to genomics expertise (e.g., genomic champions in clinical units, establishment of multi-disciplinary meetings, laboratory feedback or guardrails)
Clear escalation pathways for questions/concerns including organisational expert backup
Flags in electronic medical records to prompt timely result return
Awareness of referral pathways and when to involve genetic counselling
Use of current NPAAC recommendations for management of incidental findings
(If external) contracts specifies quality metrics for test analysis
Sufficient pathology expertise
Ensuring use of NATA-accredited laboratory
For patient risks at Step 8: Clinical application of genomic results in the context of an individual patient | Effective models of care including clinical application of results
Training and development of relevant staff to ensure skills and knowledge in clinical application of results
Credentialling and special scope of practice to provide standards for relevant practitioners
Organisational determination of who can order which tests and thus undertake results return and clinically apply results (e.g., Junior Doctor needs Consultant approval)
Design of locally appropriate access to genomics expertise (e.g., genomic champions in clinical units, establishment of multi-disciplinary meetings, laboratory feedback or guardrails)
Clear escalation pathways for questions/concerns including organisational expert backup
Patient profiles established for those undertaking testing that include consideration of future assessments (i.e., young female single patient is reviewed at a later stage when childbearing is more likely)
Where available, consider use of IT systems to support practice (e.g., prompts added to the electronic medical records for follow-up)
Clear guidelines available for management of family members stratified by risk level
For patient risks at Step 9: Family support considerations and requirements | Clear support details available relevant for the context and patient group (this will most likely vary in each department and within each hospital)
Clear guidelines available for management of family members stratified by risk level

## Dropdown lists
dropdown lists
Organisational Risk
Patient Risk
Step 1: Identification of patients who should be considered for genomic testing
Step 2: Referral process for consideration of potential testing pathways
Step 3: Consideration of genomic test options
Step 4: Assessing and undertaking consent; and legal implications
Step 5: Ordering genomic tests
Step 6: Genomic test analysis
Step 7: Interpreting genomic test results
Step 8: Clinical application of genomic results in the context of an individual patient
Step 9: Family support considerations and requirements
1
2
3
4
5